## Burndown Chart Template
Burndown Chart Template
Velocity = Total Story Points Delivered over a Sprint
Sprint 1 |  | Story Points
User Story 0 |  | 1
User Story 1 |  | 5
User Story 2 |  | 4
User Story 3 |  | 1
User Story 4 |  | 2 |  | Note: this user story wasn't delivered in Sprint 1 since the team didn't have time to complete it
User Story 5 |  | 3
| Total | 16 | Velocity Sprint 1 | 14
Sprint 2
User Story 1 |  | 2
User Story 5 |  | 3
User Story 6 |  | 3
User Story 7 |  | 3
User Story 2 |  | 2
User Story 4 |  | 2
User Story 3 |  | 3
| Total | 18 | Velocity Sprint 2 | 18
Total Story Points |  | 34 | Average Velocity | 16
Traditional
Burndown Chart
Sprint | Remaining Story Points
1 | 34
2 | 20
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 34 | 14
2 | 20 | 18
Another option
Burndown Chart
Sprint | Remaining Story Points | Story Points Delivered
1 | 34 | 14
2 | 20 | 18